## Sheet1
22092020-29092020
SCOM Report server issue | Working on SCOM report issue. | Nisha Patel
Un-used DB archival activity | DB backup has been taken and brings down whose response came. | Yogita Shettigar | done
Docker webapp hosting | shrem done : 5/12 done, SMP code issue | Harsh Patel | done
SCVMM integration with SCOM | In Process | Ravi Keshwani | done
Server recycle activity | RSDC003 is In Process,in RSDC003 : homefolder completed. rest of the servers done | Kaushal Dhora
Insurance : HP Laptops | shared damaged laptop details to account (sandip bhai). They have filed for claim 1. RSPLLT180 (Hiren Gajera) 2. RSPLLT138 (Rohit Gupta)
SACS : Installation and Testing | co-ordinating with vendor still in process.
Haver SCM server platform readyness | Server is ready with require softwares
Data movement for Petrogas project | create a small file server on RSPLWS361 and configured. Bcz they are facing issue while accessing 28 GB size of file.
Scan all servers against Ransome ware threat | Scanned all servers to find trash of ransomeware but nothing found on a single server. checked CS status as well. Looks good.
Prepared report for Quarterly review | Prepared backup reports,AD reports, FTP reports, File server reports etc.
28092020-05102020
In-Active status report | In-Active status report has been prepared and sent to HR
Xerox Printout Report | Prepared user wise Xerox prinout report and shared with amol sir.
SCOM Report server issue | Report server database issue has been resolved
Un-used DB archival activity | In Process, Acknowledge DBs' taken offline.
SCVMM integration with SCOM | Integration of SCVMM to Ops Manager completed
Server recycle activity | In Process, All folders are archived. Confirmation pending from owners of the folders
SACS : Installation and Testing | SACS configured and installed perfectly on Vaibhav's system.
Server Platform Readyness | New server for R360 is created.
05-10-2020 --- 11-10-2020
Server,office 365 admin access list | Administrator access list has been prepared for all servers and O365.
Server Recycle Project | After getting confirmation data was removed from the source servers.
SCOM Report generation | Reports have been generetaed from SCOM for the different criteria
Linux Agent Installation | SCOM agent has been installed in linux servers.
LFM Issue | Vendor Co-ordination is in process
Password change : Linux Servers | Password of all linux servers are changed
onedrive account setup | common OneDrive account has been setup for ESO team.
12-10-2020 --- 18-10-2020
LFM licene issue | LFM license started working now.
E3D license renewal | Negotiated with Ashish & license team for E3D renewal
Un-Used DBs' Archival | Reminder mail sent : No response from Kandarp Bhai
SACS license Issue | Issue has been rectified & resolved
Schedule Report Generation : SCOM | Schedule report generation & mail notification done
SACS Installation & configuration | SACS software has been installed in mayur baxani's system.
Solidwroks License Renewal | Negotiated with Nitin Vanvir (Eng. Technique) for the renewal of Solid works software
BricsCAD : Installation | Testing of BricsCAD installation done.
Xerox bill verify | Xerox bill is verified. Require to take a call with Xerox vendor
Vendor Co-ordination for BricsCAD License | Negotiation is in progress with Bhavesh Tawre (Image Graphix) for the BricsCAD license
Slow system performance issue : E3D | System performance issue has been resolved because of SSD
19102020-25102020
O365 Backup Solution | Demo Setup created. Detail document is in process
MPN License Details Updation | Update License sheet from the MPN portal
ESO license detail updation | Update ESO license in a license inventory
Naviswork Manage Installation | In Process
SCOM fine tuning | In Process
26102020-31102020
O365 backup document | Detail document has been prepared and sent via mail.
BricsCAD Issue | License server configured. It is started working.
Un Used DB removal | Un-Used DB has been archived and removed from DB server.
Server Inventory update | Server Inventory is updated
30 day In-Active user report creation | List was prepared but not found any regular in-active user.
SCSM : change management | In Progress
Xerox Details Userwise | Userwise Xerox printout details has been prepared and sent to Harshil
02112020-06112020
E3D license Installation | new E3D license has been configured in RSPLWS284
AD user external mail block check | Reviewed those users who are misplaced in external mail block group.
EMS : list feature, which are implemented, | which are not implemented, what are the benefits for that
CS Installation & Symantec Removal | CS installed in desktop based server and uninstalled symantec.
Gradle issue | It is been resolved after doing uninstall EPP.
vendor co-ordination : LFM & E3D License | co-ordinated with Aveva for LFM license
Local Administrator : Review | Prepared a department wise list for developer users.
Change request for O365 Backup
Send to Sir for approval with backup document
Scom.Admin Mail setup in SCOM report | scom.admin mail has been set up in SCOM reports
Un-authorized software Report | Prepared a un-authorized software installation report and shoot mails.
Skype Recharge | 300$ of skype recharge has been done
Logon failure report | Mail has been sent to the users
Staad Pro : Bentley | Co-ordinated with vendor of bentley for staad pro.
Local Administrator : Review | In process
Staad Pro License Comparision | Prepared a comparision for staad pro license.
Failure Login : Report | Mail has been sent to the users
ESO : software report creation | software report has been created.
24112020-28112020
Failure Login : Report | Sent mail to the users who are listed in report.
Un-Authorized software : Monitor | Sent mail to the users who are listed in report.
ESO : software report creation | software report has been created.
SCSM : Webportal | In Process
Xerox machine : support renewal | Co-ordinated with vendor of Xerox.
Vendor co-ordination : ESO | Co-ordinated with various vendor of ESO softwares.
IBM Cloud : Lite account | R&D has been performed on lite account / free tier
30-11-2020 -- 04122020
Xerox Usage Report | Userwise Xerox report has been prepared
Backup Document for O365 | Proposal PPT has been created for O365 mail backup
Failure Login : Report | Sent mail to the users who are listed in report.
Un-Authorized software : Monitor | Sent mail to the users who are listed in report.
SCSM : change request webportal | R&D was performed but no reference record found.

## Sheet2
Status
Manage | ITCG | ask rahul bhai
BricsCAD | Imaegrafix | mail to bhavesh bhai
Aveva E3D